## Product Backlog
Planned Sprints | Actual Sprints | US ID | User story description | Status | Document
Sprint 1 | Sprint 1 | US01 | As an Admin, I want to link the ticket data with Google Sheets so that the AI system can directly access and interact with the support database. | Completed
Sprint 1 | Sprint 1 | US02 | As a Data Scientist, I want to connect and preprocess past ticket records so that the data is clean and ready for analysis. | Completed
Sprint 2 | Sprint 2 | US03 | As an AI Engineer, I want to develop a Retrieval-Augmented Generation (RAG) model so that AI can generate accurate ticket responses using the internal knowledge base. | Completed
Sprint 2 | Sprint 2 | US04 | As a Support Leader, I want the LLMs to automatically categorize and prioritize support tickets so that agents can focus on resolving issues efficiently. | Completed
Sprint 2 | Sprint 2 | US05 | As a Product Owner, I want to evaluate the model on a pilot dataset so that I can measure its performance and accuracy before deployment. | Completed
Sprint 2 | Sprint 2 | US06 | As a Data Scientist, I want to clean and structure the ticket data properly so that the model receives high-quality input for training. | Completed
Sprint 3 | Sprint 3 | US07 | As a User, I want to integrate the AI chatbot into the support portal so that I can get my issues resolved instantly without waiting for an agent. | Completed
Sprint 3 | Sprint 3 | US08 | I want to integrate tools such as the RAG model and Tabular Search system into the agent interface to enhance support capabilities. | Completed
Sprint 3 | Sprint 3 | US09 | As an Agent, I want to receive real-time article and solution recommendations so that I can resolve customer tickets more quickly. | Completed
Sprint 3 | Sprint 3 | US10 | As a Manager, I want to have an analytical dashboard displaying all ticket metrics so that I can monitor performance and resolution trends effectively. | Completed
Sprint 3 | Sprint 3 | US11 | As a Manager, I want a dashboard with alert notifications so that I can easily identify and address support gaps or delays. | Completed

## Sprint backlog
US ID | Task ID | Task Description | Task Start Date | Task Completeion Date | Member
US01 | T1 | Connect the tickets data via google sheets | 2025-08-18 | 2025-08-19 | Yash Anil Mahajan
US02 | T2 | Collect and preprocess the historical data or ticket data | 2025-08-19 | 2025-08-21 | Yash Anil Mahajan
US03 | T3 | Build Rag model for ticket responses | 2025-08-21 | 2025-08-26 | Yash Anil Mahajan
US04 | T4 | Categorize tickets using LLMs | 2025-09-01 | 2025-09-06 | Yash Anil Mahajan
US05 | T5 | Test model on pilot datasets | 2025-09-06 | 2025-09-08 | Yash Anil Mahajan
US06 | T6 | Preprocess ticket data for clean input | 2025-09-08 | 2025-09-09 | Yash Anil Mahajan
US07 | T7 | Build AI chatbot to resolve user queries | 2025-09-11 | 2025-09-15 | Yash Anil Mahajan
US08 | T8 | Integrate tolls like RAG model tabulea search to agents | 2025-09-15 | 2025-09-18 | Yash Anil Mahajan
US09 | T9 | Provide real time article recommendation | 2025-09-18 | 2025-09-20 | Yash Anil Mahajan
US10 | T10 | Build analytical dashboard | 2025-09-20 | 2025-09-22 | Yash Anil Mahajan
US11 | T11 | Dashboard and slack alerts for monitoring | 2025-09-26 |  | Yash Anil Mahajan

## Meeting updates
Sprint | Day | Implementations | Actions Taken
Sprint 0 | Day 1 | Guidelines to begin the work | Begins the work
Sprint 1 | 2025-08-26 | Discussion of implementations of sprint 1 | Connected to google sheets and collected to datasets
Sprint 2 | 2025-09-09 | Reasoning behind slow accuracy | Change the chat model to groq
Sprint 3 | 2025-09-22 | Various sentiments in tickets classifications | Changed the categories to only positive, negative and neutral
Sprint 4

## Retrospection
SL | Sprint | Sprint Start Date | Sprint End Date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action Item
1 | Sprint 1 | Aug 13th | Aug 29th | Yash Anil Mahajan | Connecting to Google Sheets | Collecting the Database | Building RAG Model | Preprocessing implemented
2 | Sprint 2 | Sept 1st | Sept 10th | Yash Anil Mahajan | Categorizing Tickets | Testing Model with Pilot Dataset | Preprocessing the Data Input | Pilot dataset
3 | Sprint 3 | Sept 11th | Sept 25th | Yash Anil Mahajan | Building the AI Agent | Providing Real-time Article Recommendation | Building Analytical Dashboard | Integrated RAG search
4 | Sprint 4 | Sept 26th | Oct 10th | Yash Anil Mahajan | Monitoring alerts setup